## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Gym Locator and Booking |  | 1 month | 2021-08-25 | 2021-09-26 | 2021-09-29
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design | 2021-08-25 |  | 5 days
1.1 | Project Defination | 2021-08-25 | 2021-08-26
1.2 | Finish webpage | 2021-08-26 | 2021-08-28
1.3 | Project Design | 2021-08-28 | 2021-08-29
2 | Coding | 2021-08-30 |  | 22 days
2.1 | Phase 1 | 2021-08-30 | 2021-09-08
2.2 | Phase 2 | 2021-09-09 | 2021-09-18
2.3 | Additional Features | 2021-09-18 | 2021-09-20
3 | Testing | 2021-09-21 |  | 2 days
3.1 | Phase 1 Testing | 2021-09-21 | 2021-09-22
3.2 | Modification /Any changes | 2021-09-22 | 2021-09-22
3.3 | Phase 2 Testing | 2021-09-22 | 2021-09-23
3.4 | Modification /Any changes | 2021-09-22 | 2021-09-23
3.5 | Final Testing | 23sep22021 | 2021-09-23
4 | Documentation | 24/9/2021 to 26/9/2021 |  | 2 days
4.1 | User Guide | 2021-09-25 | 2021-09-25
4.2 | Presentation | 2021-09-26 | 2021-09-26

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Backend Code
| Member Name | Tarun kumar(TL)
| PRN No | 210543181111
| Description | J2EE,MySQL
2 | Role | Backend Code
| Member Name | Rohit Sharma
| PRN No | 210543181081
| Description | J2EE,MySQL
3 | Role | Front End Technology
| Member Name | Anmol Gangil
| PRN No | 210543181008
| Description | HTML,Thymleaf,CSS,Bootstrap,JS,jQuery
4 | Role | Front End Technology
| Member Name | Bhushan Ghodeswar
| PRN No | 210543181027
| Description | HTML,Thymleaf,CSS,Bootstrap,JS,jQuery